## Sheet1
Risk Category | Risk Description | Likelihood | Impact | Mitigation Strategy
Technical Risks | Challenges in integrating Blockchain with Python | Medium | High | Conduct feasibility study, use well-documented frameworks
| API performance issues under high load | Medium | High | Optimize code, conduct stress testing
Security Risks | Vulnerabilities in Blockchain implementation | Medium | High | Follow best security practices, use robust encryption
| API data breaches | Low | High | Implement authentication and access controls
Project Management Risks | Scope creep due to evolving requirements | High | Medium | Define clear scope, manage changes with a process
| Volunteer-based workforce delays | High | Medium | Set realistic deadlines, maintain strong communication
Financial Risks | Budget overruns | Low | Medium | Use open-source tools, monitor expenses closely
Operational Risks | Issues in deployment and maintenance | Medium | High | Develop comprehensive deployment and rollback plans
Stakeholder Risks | Lack of adoption by end users | Medium | Medium | Conduct early user testing and feedback sessions